## Report
No. | Product Deliverables | Task | GiangHHT | ManhOT | VuongNQ | Size
1 | Report1 - Introduction | Project Information |  | O |  | 1
|  | Introduction |  |  | O | 1
|  | Current Situation |  |  | O | 1
|  | Problem Definition |  |  | O | 1
Proposed Solution
|  | Feature functions | O |  |  | 1
|  | Advantages and disadvantages | O |  |  | 1
|  | Functional Requirements |  | O |  | 1
|  | Roles and Responsibility |  | O |  | 1
|  | Review and merge document | O |  |  | 2
2 | Report2- Software Project Management Plan | Problem Definition
|  | Name of this Capstone Project |  |  | O | 1
|  | Problem Abstract |  |  | O | 1
Project Overview
|  | Current Situation |  |  | O | 1
|  | The Proposed System |  | O |  | 1
|  | Boundaries of the System |  | O |  | 1
|  | Development Environment |  | O |  | 1
|  | Project organization | O |  |  | 1
|  | Project Management Plan |  | O |  | 1
|  | Coding Convention |  | O |  | 1
|  | Review and merge document | O |  |  | 2
3 | Report 3- Software Requirement Specification | User Requirement Specification |  |  | O | 2
System Requirement Specification
|  | External Interface Requirements |  |  | O | 1
|  | System Overview Use Case | O |  |  | 2
List of Use Case
|  | <Guest> Login |  | O |  | 1
|  | <Guest> Search product |  | O |  | 1
|  | <Guest> View product detail |  | O |  | 1
|  | <Guest> Make order |  | O |  | 1
|  | <Authenticated user> Logout |  | O |  | 1
|  | <Authenticated user> Search product |  | O |  | 1
|  | <Authenticated user> View product detail |  | O |  | 1
|  | <Authenticated user> Change personal information |  | O |  | 1
|  | <Authenticated user> Change password |  | O |  | 1
|  | <Authenticated user> Reset password |  | O |  | 1
|  | <System> Get notification |  | O |  | 1
|  | <Customer> Make order |  | O |  | 1
|  | <Customer> Edit order |  | O |  | 1
|  | <Customer> View order detail |  | O |  | 1
|  | <Customer> Cancel order |  | O |  | 1
|  | <Customer> Confirm order |  | O |  | 1
|  | <Staff> Add order | O |  |  | 1
|  | <Staff> Edit order | O |  |  | 1
|  | <Staff> View order detail | O |  |  | 1
|  | <Staff> Approve order | O |  |  | 1
|  | <Staff> Change order state | O |  |  | 1
|  | <Staff> Export bill | O |  |  | 1
|  | <Staff> Cancel order | O |  |  | 1
|  | <Staff> Export more material for order | O |  |  | 1
|  | <Staff> Add input material |  |  | O | 1
|  | <Staff> Edit input material |  |  | O | 1
|  | <Staff> Change input material state |  |  | O | 1
|  | <Staff> Add input bill |  |  | O | 1
|  | <Staff> Edit input bill |  |  | O | 1
|  | <Staff> Change material status |  | O |  | 1
|  | <Staff> Add material |  | O |  | 1
|  | <Staff> Edit material |  | O |  | 1
|  | <Staff> Add product |  | O |  | 1
|  | <Staff> Edit product |  | O |  | 1
|  | <Staff> Change product status |  | O |  | 1
|  | <Manager> Edit store information |  | O |  | 1
|  | <Manager> Edit store config |  | O |  | 1
|  | <Manager> Add new staff |  |  | O | 1
|  | <Manager> Change staff status |  |  | O | 1
|  | <Manager> Change customer status |  |  | O | 1
|  | <Manager> Change customer account to loyal |  |  | O | 1
|  | <Manager> Add new supplier |  |  | O | 1
|  | <Manager> Edit supplier information |  |  | O | 1
|  | <Manager> Change supplier status |  |  | O | 1
|  | <Manager> Update VAT Tax rate | O |  |  | 1
|  | <Manager> Update Excise tax rate | O |  |  | 1
|  | <Manager> Review income by time | O |  |  | 1
|  | <Manager> Review income by product | O |  |  | 1
|  | <Manager> Review income by customer | O |  |  | 1
|  | <Manager> Create VAT Tax Declacration | O |  |  | 1
|  | <Manager> Create Excise Tax Declacration | O |  |  | 1
|  | Software System Attribute | O |  |  | 1
|  | Conceptual Diagram | O |  |  | 1
|  | Review and merge document | O |  |  | 2
4 | Report 4- Software Design Description | System Architectural Design | O |  |  | 2
|  | Component Diagram | O |  |  | 1
|  | Class Diagram | O |  |  | 2
|  | Class Diagram Explanation |  | O |  | 1
Interactive Diagram
|  | <Guest> Make order |  | O |  | 1
|  | <Authenticated user> Change personal information |  | O |  | 1
|  | <Authenticated user> Change password |  | O |  | 1
|  | <Authenticated user> Reset password |  | O |  | 1
|  | <Authenticated user> Search product |  | O |  | 1
|  | <Authenticated user> View product detail |  | O |  | 1
|  | <System> Get notification |  | O |  | 1
|  | <Customer> Make order |  | O |  | 1
|  | <Customer> Confirm order |  | O |  | 1
|  | <Customer> Cancel order |  | O |  | 1
|  | <Customer> Edit order |  | O |  | 1
|  | <Staff> Approve order | O |  |  | 1
|  | <Staff> Add order | O |  |  | 1
|  | <Staff> Cancel order | O |  |  | 1
|  | <Staff> Edit order | O |  |  | 1
|  | <Staff> Change order status | O |  |  | 1
|  | <Staff> Export bill | O |  |  | 1
|  | <Staff> Export more material for order | O |  |  | 1
|  | <Staff> Add input material |  |  | O | 1
|  | <Staff> Edit input material |  |  | O | 1
|  | <Staff> Discard input material |  |  | O | 1
|  | <Staff> Add input bill |  |  | O | 1
|  | <Staff> Edit input bill |  |  | O | 1
|  | <Staff> Change material status |  | O |  | 1
|  | <Staff> Add material |  | O |  | 1
|  | <Staff> Edit material |  | O |  | 1
|  | <Staff> Add product |  | O |  | 1
|  | <Staff> Edit product |  | O |  | 1
|  | <Staff> Change product status |  | O |  | 1
|  | <Manager> Edit store information |  | O |  | 1
|  | <Manager> Edit store config |  | O |  | 1
|  | <Manager> Add new staff |  |  | O | 1
|  | <Manager> Change staff status |  |  | O | 1
|  | <Manager> Change customer status |  |  | O | 1
|  | <Manager> Change customer account to loyal |  |  | O | 1
|  | <Manager> Add new supplier |  |  | O | 1
|  | <Manager> Edit supplier information |  |  | O | 1
|  | <Manager> Change supplier status |  |  | O | 1
|  | <Manager> Update VAT Tax rate | O |  |  | 1
|  | <Manager> Update Excise tax rate | O |  |  | 1
|  | <Manager> Review income by time | O |  |  | 1
|  | <Manager> Review income by product | O |  |  | 1
|  | <Manager> Review income by customer | O |  |  | 1
|  | <Manager> Create VAT Tax Declacration | O |  |  | 1
|  | <Manager> Create Excise Tax Declacration | O |  |  | 1
Interface
Customer/Guest Interface Design
|  | Home page |  |  | O | 1
|  | User Login |  |  | O | 1
|  | Product page |  |  | O | 1
|  | Check cart |  |  | O | 1
|  | View information in cart |  |  | O | 1
|  | Confirm order |  |  | O | 1
|  | Add customer information to order |  |  | O | 1
|  | Change personal information |  |  | O | 1
|  | Change password |  |  | O | 1
|  | Staff/Manager Interface Design |  |  |  | 1
|  | View order list | O |  |  | 1
|  | Staff add product to order | O |  |  | 1
|  | Add customer to order | O |  |  | 1
|  | Checkout with new customer | O |  |  | 1
|  | Confirm order | O |  |  | 1
|  | View input bill list |  | O |  | 1
|  | Add new input bill |  | O |  | 1
|  | View input material list |  | O |  | 1
|  | View input material detail |  | O |  | 1
|  | Add new input material |  | O |  | 1
|  | Review income by time | O |  |  | 1
|  | Review income weekly detail | O |  |  | 1
|  | VAT Tax declaration - Applendix 1 | O |  |  | 1
Database design
|  | Entity relationship diagram | O |  |  | 2
|  | Entity dictionary |  | O |  | 1
Algorithms
|  | Order state | O |  |  | 2
|  | Review and merge document | O |  |  | 2
5 | Report 5 - Software Implementation and Test Document | はじめに |  |  | O
データベース関係ダイアグラム
|  | ウェブアプリケーション物理的な ダイアグラム | O |  |  | 2
|  | ウェブアプリケーションデータ辞書 |  | O |  | 1
|  | パフォーマンス対策 | O |  |  | 2
|  | テスト計画 | O |  |  | 1
システムテストのテストケース
ウェブシステムのテストケース
|  | 「顧客」製品を注文すること |  |  | O | 1
|  | 「ゲスト」製品を注文すること |  |  | O | 1
|  | 「人員」送り状を造ること |  |  | O | 1
|  | ユーザログイン |  |  | O | 1
|  | 「人員」送り状を承認すること |  |  | O | 1
|  | 「人員」送り状の状態を変化すること |  |  | O | 1
|  | 「人員」入力原料を付加すること |  |  | O | 1
|  | 「人員」入力原料を捨てること |  |  | O | 1
6 | Report 6 - Software User's Manual | インストレーションガイド |  |  | O
|  | ユーザーガイド |  | O |  | 2
|  | ログイン |  |  | O | 1
|  | 製品を注文すること |  |  | O | 1
|  | カートに製品を追加すること |  |  | O | 1
|  | かーとをチェックすること |  |  | O | 1
|  | カーとの精細 |  |  | O | 1
|  | 送り状を確認すること |  |  | O | 1
|  | 送り状に顧客の情報を充実すること |  |  | O | 1
|  | 送り状に顧客の情報を充実すること |  |  | O | 1
|  | 「人員」送り状を造ること |  |  | O | 1
|  | 送り状に顧客を追加すること |  |  | O | 1
|  | 新い顧客の口座で送り状をチェックアウト |  |  | O | 1
|  | 入力法案 リスク |  |  | O | 1
|  | 新入力法案を造ること |  |  | O | 1
|  | 入力原料 リスクを見る |  |  | O | 1
|  | 入力原料 の精細を見ること |  |  | O | 1
|  | 新入力原料を造ること |  |  | O | 1
7 | Authentication and Account | <Guest>Login |  | O |  | 1
|  | <Authenticated User>Logout |  | O |  | 1
|  | <Authenticated User>Edit own profile information |  | O |  | 1
|  | <Authenticated User> Reset password |  | O |  | 1
|  | <Authenticated User>Change password |  | O |  | 1
8 | Order Online | <Guest, Customer> Make order |  | O |  | 1
|  | <Guest, Customer> Search product in Order Online System |  | O |  | 1
|  | <Guest, Customer> View product detail in Order Online System |  | O |  | 1
|  | <Customer> Edit order |  | O |  | 1
|  | <Customer> Cancel order |  | O |  | 1
|  | <Customer> Confirm order |  | O |  | 1
9 | <Staff> Manage Product | List all of product |  | O |  | 1
|  | Add new product |  | O |  | 1
|  | Edit the product |  | O |  | 1
|  | View product detail in Manage System |  | O |  | 1
|  | Change product status |  | O |  | 1
10 | <Staff>Manage Order | List of order | O |  |  | 1
|  | View order detail | O |  |  | 1
|  | Edit order | O |  |  | 1
|  | Add order | O |  |  | 1
|  | Cancel order | O |  |  | 1
|  | Approve order | O |  |  | 1
|  | Change order status | O |  |  | 1
|  | List of shortage of material for order | O |  |  | 1
|  | Export Bill | O |  |  | 1
|  | Create customer account | O |  |  | 1
11 | <Staff>Manage Bill | Add input bill |  |  | O | 1
|  | Edit input bill |  |  | O | 1
|  | List all input bill |  |  | O | 1
12 | <Staff>Manage Input Material | Show input material list |  |  | O | 1
|  | Add discard for input material |  |  | O | 1
|  | Add new input material |  |  | O | 1
|  | Edit input material |  |  | O | 1
13 | <Staff>Manage Supplier | List all suppliers with name, address, phone |  |  | O | 1
|  | Change supplier status |  |  | O | 1
|  | Add supplier |  |  | O | 1
|  | Edit supplier |  |  | O | 1
14 | <Staff>Manage Product Material | Add product material |  | O |  | 1
|  | Edit product material |  | O |  | 1
|  | View product material detail |  | O |  | 1
|  | Change product material status |  | O |  | 1
15 | <Manager>Tax | Edit tax rate of VAT and Excise tax | O |  |  | 1
|  | Create VAT Tax Declaration | O |  |  | 2
|  | Create Excise Tax Declaration | O |  |  | 2
16 | <Manager>Statistic | Review income by time | O |  |  | 3
|  | Review income by good | O |  |  | 3
|  | Review revenue by customer | O |  |  | 3
17 | <Manager>Store information | Edit store information |  | O |  | 1
|  | Edit system config - Min order quantity - Discount price depend on quantity - Max price for product |  | O |  | 2
|  | Set loyal for customer |  |  | O | 1
18 | <Manager>Manage Staff | List all staff |  |  | O | 1
|  | Change staff status |  |  | O | 1
|  | Add new staff |  |  | O | 1
|  | <Staff>Edit staff information |  |  | O | 1
19 | <Staff> Manage Customer | List all customer |  |  | O | 1
|  | Change customer status |  |  | O | 1
20 | <Manager>Manage Other Expense | List all of other expense | O |  |  | 1
|  | Add new other expense | O |  |  | 1
|  | Edit other expense | O |  |  | 1
|  | Delete other expense | O |  |  | 1
21 | <Manager> Manage Category |  |  | O |  | 2
22 | Notification | Notification to staff when there are new orders |  | O |  | 1
|  | Notification to customer when the order status is changed by staff |  | O |  | 1
|  | Notification to staff when the material quantity is below standard quantity |  | O |  | 1
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task

## Implement
No. | Product Deliverables | Task | GiangHHT | ManhOT | VuongNQ | Priority 1 -> 5 | Size | Status | Deadline | Complete Date | Comment |  |  | Edit Use Case Description and Sequence Diagram
1 | Authentication and Account | <Guest>Login |  | O |  |  |  | Done |  |  |  | Toàn bộ | 58
|  | <Authenticated User>Logout |  | O |  |  |  | Done |  |  |  | Hoàn thành | 52
|  | <Authenticated User>Edit own profile information |  | O |  | 3 | 1 | Done | 2015-10-30 |  |  | Tiến độ | 89.6552
|  | <Authenticated User> Reset password |  | O |  |  |  | Done | 2015-11-10 |  | Vẽ thêm UseCase
|  | <Authenticated User>Change password |  | O |  | 5 | 1 | Done | 2015-10-30
2 | Order Online | <Guest, Customer> Make order |  | O |  | 3 | 4 | Done | 2015-11-02 |  |  |  |  | Done ( Edit and review)
|  | <Guest, Customer> Search product in Order Online System |  | O |  | 5 | 2 | Done | 2015-10-31 |  |  |  |  | Done ( Edit and review)
|  | <Guest, Customer> View product detail in Order Online System |  | O |  |  |  | Done | [5 empty] | Done ( Edit and review)
|  | <Customer> Edit order |  | O |  |  |  | Done | [5 empty] | Done ( Edit and review)
|  | <Customer> Cancel order |  | O |  |  |  | Done | [5 empty] | Done ( Edit and review)
|  | <Customer> Confirm order |  | O |  |  |  | Done | [5 empty] | Done ( Edit and review)
|  | Edit template |  | O |  | 5 | 5 | Done | 2015-10-29
3 | <Staff> Manage Product | List all of product (Not have Use Case) |  | O |  |  |  | Done
|  | Add new product Add material to product |  | O |  | 4 | 4 | Done | 2015-11-10
|  | Edit the product Edit material to product |  | O |  | 4 | 4 | Done | 2015-11-10
|  | View product detail in Manage System |  | O |  | 4 |  | Done
|  | Change product status (New Use Case) |  | O |  |  |  | Done
4 | <Staff>Manage Order | List of order (Not have use case) | O |  |  | 5 | 1 | Done | 2015-10-27
|  | View order detail | O |  |  | 5 | 1 | Done | 2015-10-27
|  | Edit order | O |  |  | 5 | 1 | Done | 2015-10-29 |  |  |  |  | Done (Edit)
|  | Add order | O |  |  | 5 | 1 | Done | 2015-10-28 |  |  |  |  | Done (Edit)
|  | Cancel order | O |  |  | 5 | 1 | Done | 2015-10-29 |  |  |  |  | Done (Edit)
|  | Approve order | O |  |  | 5 | 1 | Done | 2015-10-28 |  |  |  |  | Done (Edit)
|  | Change order status | O |  |  | 5 | 1 | Done | 2015-10-30 |  |  |  |  | Done (Edit)
|  | List of shortage of material for order (New Use Case) | O |  |  | 3 | 1 | Done | 2015-10-31
|  | Export Bill | O |  |  | 5 | 1 | Done | 2015-10-30 |  |  |  |  | Done (Edit)
|  | Create customer account | O |  |  | 3 | 1 | Done | 2015-10-31
5 | <Staff>Manage Bill | Add input bill |  |  | O |  | 2 | Done | 2015-11-10 |  | Còn hình |  |  | Còn UC 26/11/2015
|  | Edit bill (InputBill & OutputBill) |  |  | O |  | 2 | Còn hình | 2015-11-11 |  |  |  |  | Còn UC 26/11/2015
|  | List all bill (InputBill & OutputBill) with code, type, create time, total amount and sort decending create time (Not have in Use Case) Search bill by code, type, create time filter |  |  | O | 3 | 1 | Done | 2015-11-09
6 | <Staff>Manage Input Material | Show input material list (Not have in Use Case) |  |  | O | 3 | 1 | Done | 2015-10-28
|  | Add discard for input material |  |  | O | 3 | 1 |  | 2015-11-13 |  |  |  |  | Còn UC 26/11/2015
|  | Add new input material |  |  | O | 3 | 2 | Done | 2015-10-29 |  |  |  |  | Còn UC 26/11/2015
|  | Edit input material |  |  | O | 3 | 2 | Done | 2015-10-30 |  |  |  |  | Còn UC 26/11/2015
7 | <Staff>Manage Supplier | List all suppliers with name, address, phone (Not have in Use Case) |  |  | O | 3 | 1 | Done | 2015-10-31 |  | Add "Thêm nhà cung cấp" button
|  | Change supplier status |  |  | O | 3 | 1 | Done | 2015-10-31 |  |  |  |  | X
|  | Add supplier |  |  | O | 3 | 2 | Done | 2015-11-01 |  | Số điện thoại; Mã số thuế không được type = number |  |  | X
|  | Edit supplier |  |  | O | 3 | 2 | Done | 2015-11-02 |  | Noty thành công chuyển vị trí từ bottomLeft sang topCenter |  |  | X
8 | <Staff>Manage Product Material | Add product material |  | O |  |  |  | Done
|  | Edit product material |  | O |  | 3 | 1 | Done | 2015-11-11
|  | View product material detail | [5 empty] | Done
|  | Noty when the material is below standard quantity |  | O |  |  |  |  | 2015-11-21
|  | Change product material status |  | O |  | 3 | 1 | Done | 2015-11-11
9 | <Manager>Tax | Edit tax rate of VAT and Excise tax | O |  |  | 4 | 2 | Done 50% | 2015-11-21
|  | Create VAT Tax Declaration | O |  |  | 3 | 4 |  | 2015-11-19
|  | Create Excise Tax Declaration | O |  |  | 3 | 4 |  | 2015-11-20
10 | <Manager>Statistic | Review income by time | O |  |  | 3 | 4 | Done | 2015-11-12
|  | Review revenue by good | O |  |  | 3 | 4 | Done | 2015-11-15
|  | Review revenue by customer | O |  |  | 3 | 4 | Done | 2015-11-17
9 | <Manager>Store information | Edit store information |  | O |  | 1 | 1 | Done | 2015-11-12
|  | Edit system config - Min order quantity - Discount price depend on quantity - Max price for product |  | O |  | 1 | 1 | Done | 2015-11-14
|  | Set loyal for customer |  |  | O | 1 | 1 | Done | 2015-11-13 |  |  |  |  | X
12 | <Manager>Manage Staff | List all staff(Not in Use Case) |  |  | O | 1 | 1 | Done | 2015-11-06
|  | Change staff status |  |  | O | 1 | 1 | Done | 2015-11-06 |  |  |  |  | X
|  | Add new staff |  |  | O | 1 | 2 | Done | 2015-11-12
|  | <Staff>Edit staff information |  |  | O |  |  | Done | 2015-11-04 |  |  |  |  | X
13 | <Staff> Manage Customer | List all customer (Not in Use Case) |  |  | O | 1 | 1 | Done | 2015-11-03
|  | Change customer status |  |  | O | 1 | 1 | Done | 2015-11-03 |  |  |  |  | X
14 | <Manager>Manage Other Expense | List all of other expense | O |  |  |  |  | Done | 2015-11-13
|  | Add new other expense | O |  |  |  |  | Done | 2015-11-13
|  | Edit other expense | O |  |  |  |  | Done | 2015-11-13
|  | Delete other expense | O |  |  |  |  | Done | 2015-11-13
15 | <Manager> Manage Category |  |  | O |  |  |  | Done | 2015-11-15
16 | Notification | Notification to staff when there are new orders |  | O
|  | Notification to customer when the order status is changed by staff |  | O
|  | Notification to staff when the material quantity is below standard quantity |  | O
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5